## Status Report
Status Report for Team 4
Project | Movie Recommendation | Status: (Red/Yellow/Green)
Date: | 2024-05-20 | Overall Status: | Green
Contact: | Isaac Rawlins-Read | Explanation: | Development is going smoothly, just need to implement movie retrieval and the persistent database, API connection
Prepared By: | Isaac Rawlins-Read
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Isaac | Setup codebase
Isaac | Implement signup system
Isaac | Implement login system
Isaac | Implement session handling
Shabna | Implement genre preference editing
Kojo | Implement movie fetching from API
Shabna | Implement delete profile
Shabna | Implement genre preference removing
Ruchita | Implement movies by prefrences
Ruchita | Implement Movie by Genre
Ruchita | Implement Movies by Ratings
ID # | Key Issues | Action Plan |  |  | Status
1 | Merge conflict in preference | Fix the list->hashmap mapping function |  |  | Resolved
Critical Milestones |  | Health | Due Date | Comment/Status %
Implement signup system |  | Green | 2024-05-20 | Completed
Implement login system |  | Green | 2024-05-20 | Completed
Implement session handling |  | Green | 2024-05-20 | Completed
Implement genre preference handling |  | Green | 2024-05-20 | Completed
Implement database |  | Green | 2024-05-20 | Not yet started
Implement movie retrieval system |  | Green | 2024-05-21 | On track
Implement movie favourites system |  | Green | 2024-05-21 | On track
Unit test signup |  | Green | 2024-05-21 | On track
Unit test login/session |  | Green | 2024-05-22 | On track
Unit test genre preference handling |  | Green | 2024-05-22 | Not yet started
Unit test movies by ratings |  | Green | 2024-05-21 | Not yet started
Unit test Movies by preferences |  | Green | 2024-05-21 | Not yet started
Unit test movies by genre |  | Green | 2024-05-21 | Not yet started
Unit test delete user profile |  | Green | 2024-05-21 | Not yet started
Implement movies by ratings |  | Green | 2024-05-20 | On track
Unit test remove genre preferences |  | Green | 2024-05-21
Write presentation |  | Green | 2024-05-23 | Not yet started
Write flowchart |  | Green | 2024-05-20 | On Track
Write database ERD |  | Green | 2024-05-23
Class UML Diagram |  | Green | 2024-05-23 | On Track
User stories |  | Green | 2024-05-20