## Status Report
Status Report for Team 4
Project | Movie Recommendation | Status: (Red/Yellow/Green)
Date: | 2024-05-22 | Overall Status: | Green
Contact: | Shabna Seethi | Explanation: | Development is going smoothly, Working on unit testing of movie and genre functions.
Prepared By: | Shabna Seethi
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Isaac | Setup codebase
Isaac | Implement signup system
Isaac | Implement login system
Isaac | Implement session handling
Shabna | Implement genre preference editing
Kojo | Implement movie fetching from API
Shabna | Implement delete profile
Shabna | Implement genre preference removing
Shabna | Implement Add Favourite Movies
Ruchita | Implement movies by prefrences
Ruchita | Implement Movie by Genre
Shabna | Unit Test add favourite movies
Shabna | Unit test genre preferences
Ruchita | Implement Movies by Ratings
Isaac | Unit test login
Isaac | Unit test create user
Isaac | Write user stories (this had already been done)
ID # | Key Issues | Action Plan |  |  | Status
1 | Merge conflict in preference | Fix the list->hashmap mapping function |  |  | Resolved
Critical Milestones |  | Health | Due Date | Comment/Status %
Implement signup system |  | Green | 2024-05-20 | Completed
Implement login system |  | Green | 2024-05-20 | Completed
Implement session handling |  | Green | 2024-05-20 | Completed
Implement genre preference handling |  | Green | 2024-05-20 | Completed
Implement database |  | Yellow | 2024-05-20 | Expectation to complete 22 May
Implement movie retrieval system |  | Green | 2024-05-21 | Completed
Implement movie favourites system |  | Green | 2024-05-21 | Completed
Unit test signup |  | Green | 2024-05-21 | Completed
Unit test login/session |  | Green | 2024-05-22 | Completed
Unit test genre preference handling |  | Green | 2024-05-22 | Completed
Unit test movies by ratings |  | Green | 2024-05-21 | On track
Unit test Movies by preferences |  | Green | 2024-05-21 | On track
Unit test movies by genre |  | Green | 2024-05-21 | On track
Unit test delete user profile |  | Green | 2024-05-21 | Completed
Implement movies by ratings |  | Green | 2024-05-20 | Completed
Unit test remove genre preferences |  | Green | 2024-05-21 | Completed
Write presentation |  | Green | 2024-05-23 | On track
Write flowchart |  | Green | 2024-05-20 | Completed
Write database ERD |  | Green | 2024-05-23 | Completed
Class UML Diagram |  | Green | 2024-05-23 | Completed
User stories |  | Green | 2024-05-20 | Completed
Research React/Frontend tech |  | Green | 2024-05-23 | Not yet started
Implement Frontend |  | Green | 2024-05-23 | Not yet started
Green